## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | Candidate Registration, Login & Session Authentication | MUST | None | Ritesh Lande | Completed
Sprint 1 | Sprint 1 | US-02 | System Permissions Setup & Pre-Exam Device Check | MUST | US-01 | Ritesh Lande | Completed
Sprint 2 | Sprint 2 | US-03 | OpenCV Real-Time Face Detection & Proctoring Engine | MUST | US-02 | Ritesh Lande | Completed
Sprint 2 | Sprint 2 | US-04 | Browser Security Violation Logger (Tab Switch / Blur) | MUST | US-01 | Ritesh Lande | Completed
Sprint 3 | Sprint 3 | US-05 | Pandas-Powered Weighted Integrity Risk Scoring Engine | MUST | US-03, US-04 | Ritesh Lande | Completed
Sprint 3 | Sprint 3 | US-06 | Real-Time Draft Answer Autosaving & Timer Countdown | MUST | US-01 | Ritesh Lande | Completed
Sprint 4 | Sprint 4 | US-07 | Candidate Dashboard & Chart.js Performance Analytics | SHOULD | US-05 | Ritesh Lande | Completed
Sprint 4 | Sprint 4 | US-08 | CSV Exam History Data Export Functionality | COULD | US-07 | Ritesh Lande | Completed
Sprint 4 | Sprint 4 | US-09 | Assessment Completion Certificate Generator | COULD | US-07 | Ritesh Lande | Completed
Sprint 4 | Sprint 4 | US-10 | 3-Mode Responsive Theme Engine (System, Light, Dark) | WONT | None | Ritesh Lande | Completed

## Sprint Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours)
US-01 | TSK-101 | Implement Flask Login & Register Blueprint | 2026-06-15 | 2026-06-17 | Ritesh Lande | Development | Closed | 12
US-01 | TSK-102 | Create SQLite User Table & Password Hashing | 2026-06-16 | 2026-06-18 | Ritesh Lande | Database | Closed | 8
US-02 | TSK-201 | Build Pre-Exam System Check UI & Camera Stream | 2026-06-19 | 2026-06-21 | Ritesh Lande | Development | Closed | 10
US-02 | TSK-202 | Integrate Screen Share & Fullscreen Toggle | 2026-06-21 | 2026-06-22 | Ritesh Lande | Development | Closed | 6
US-03 | TSK-301 | Implement OpenCV Base64 Frame Processing API | 2026-06-23 | 2026-06-25 | Ritesh Lande | AI Development | Closed | 16
US-04 | TSK-401 | Add JS VisibilityChange & Window Blur Listeners | 2026-06-26 | 2026-06-27 | Ritesh Lande | Development | Closed | 8
US-05 | TSK-501 | Develop Pandas Weighted Integrity Calculation | 2026-06-28 | 2026-06-30 | Ritesh Lande | Analytics | Closed | 14
US-06 | TSK-601 | Create Draft Answer Autosave AJAX Endpoint | 2026-07-01 | 2026-07-02 | Ritesh Lande | Development | Closed | 8
US-07 | TSK-701 | Build Candidate Dashboard & Chart.js Visuals | 2026-07-03 | 2026-07-05 | Ritesh Lande | Frontend | Closed | 12
US-08 | TSK-801 | Implement History CSV Export Route | 2026-07-06 | 2026-07-06 | Ritesh Lande | Development | Closed | 4
US-09 | TSK-901 | Design & Render Certificate Template | 2026-07-07 | 2026-07-08 | Ritesh Lande | Frontend | Closed | 6
US-10 | TSK-1001 | Implement 3-Mode Dark/Light Theme Switcher | 2026-07-09 | 2026-07-10 | Ritesh Lande | UI Styling | Closed | 6

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | SQLite database lock during session setup | Implemented connection pooling & helper functions in models.py
Sprint 2 | Day 5 | OpenCV base64 frame decoding latency | Optimized in-memory np.frombuffer and reduced frame check interval to 4s
Sprint 3 | Day 8 | TypeError on int(submission_id) when None | Added numeric validation guard: int(sub_id) if sub_id and str(sub_id).isdigit() else 0
Sprint 4 | Day 12 | Unclosed div tag in dashboard history pane | Fixed HTML nesting hierarchy in dashboard.html and verified display classes

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-06-15 | 2026-06-22 | Ritesh Lande | Modular Flask Blueprints | Hardcoding secret keys | Continuous unit testing | Organized routes into auth, exam, events blueprints
2 | Sprint 2 | 2026-06-23 | 2026-06-30 | Ritesh Lande | Asynchronous AJAX APIs | Blocking main looper thread | Real-time proctoring logs | Integrated async fetch API for violation logging
3 | Sprint 3 | 2026-07-01 | 2026-07-08 | Ritesh Lande | Pandas DataFrame scoring | Silent try-except suppression | Robust error logging | Wrapped integrity calculations in top-level exception guards
4 | Sprint 4 | 2026-07-09 | 2026-07-15 | Ritesh Lande | Responsive Theme Testing | Direct inline dark styles | Clean CSS variable design | Implemented 3-mode theme switcher with CSS custom properties