## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Ritesh Lande | 2026-06-28 | TypeError on int(submission_id) when submission_id is None in integrity_scoring.py | Sprint 3 | Ritesh Lande | Logical | Added numeric validation guard: int(sub_id) if sub_id and str(sub_id).isdigit() else 0 | 2026-06-28 | Closed | Resolved edge case for invalid/None submission IDs
2 | Ritesh Lande | 2026-07-03 | Unclosed <div> tag in history-pane hiding Results and Performance tabs on dashboard | Sprint 4 | Ritesh Lande | User Interface | Added missing closing </div> tag at line 417 and separated tab panes cleanly | 2026-07-03 | Closed | Tabs now switch display block/none correctly
3 | Ritesh Lande | 2026-07-05 | Hardcoded padding-left: 280px on flash container in base.html pushing result page alerts off-screen | Sprint 4 | Ritesh Lande | User Interface | Restricted 280px left padding offset to exam.dashboard route endpoint only | 2026-07-05 | Closed | Result page alerts now render centered
4 | Ritesh Lande | 2026-07-06 | reportMissingImports Pylance IDE warning on Flask import in app/routes/exam.py | Sprint 4 | Ritesh Lande | Standards | Created .vscode/settings.json pointing to Python interpreter and added # type: ignore | 2026-07-06 | Closed | Pylance warning resolved
5 | Ritesh Lande | 2026-07-07 | Inline style background color on Remember Me checkbox breaking checkmark contrast in Light Mode | Sprint 4 | Ritesh Lande | User Interface | Created custom .form-check-input and .form-check-label CSS rules in style.css | 2026-07-07 | Closed | Checkbox checkmark now high-contrast in both themes
6 | Ritesh Lande | 2026-07-08 | reportMissingModuleSource warning on import pandas as pd in app/integrity_scoring.py | Sprint 4 | Ritesh Lande | Standards | Added # type: ignore[import-untyped] annotation to pandas import line | 2026-07-08 | Closed | IDE diagnostic squiggles cleared
7 | Ritesh Lande | 2026-07-09 | ZeroDivisionError risk in face_presence_ratio calculation when total_log_count is 0 | Sprint 4 | Ritesh Lande | Logical | Applied max(1, checks_param, total_log_count, no_face_count) bounds calculation | 2026-07-09 | Closed | Scoring engine verified ZeroDivision safe

## Sheet2
Logical
User Interface
Maintainability
Standards
Others